## MVP Dashboard
MVP QA Dashboard — готовність PC/Web + Android
Заповнюй Status у листі “MVP Test Matrix” та дефекти у “Defects”. Dashboard і Release Gate рахуються автоматично.
KPI | Value |  | Platform | Total | Failed MVP Gate
Total tests |  |  | Cross-platform
PASS |  |  | PC/Web
FAIL |  |  | Android
BLOCKED |  |  | AI/RAG
NOT STARTED |  |  | Release
IN PROGRESS
MVP gate tests |  |  | Priority | Total | FAIL
MVP gate failed |  |  | P0
Open P0 defects |  |  | P1
Release gates passed |  |  | P2
Release gates total |  |  | P3
Gate pass ratio
Рекомендований порядок проходження
1 | Code / dependency / secrets | Прибрати blocker-и ще до runtime | P0/P1 findings = 0
2 | Build / release config | Отримати відтворюваний production build | Clean release build PASS
3 | Core functional + data | CRUD, import/export, migration, recovery | Core gate tests = 100% PASS
4 | Network / offline | Пережити offline, reconnect, 429/500 | No data loss / duplicate sync
5 | Security / privacy | SAST + dynamic + logs/storage | Critical/High exploitable = 0
6 | Performance / memory | Startup, latency, leaks, stress | Budgets met; no unbounded leaks
7 | PC/Web matrix | Browsers, DPI, filesystem, Windows env | Supported PC matrix PASS
8 | Android matrix | Lifecycle, permissions, WebView, devices, signing | Supported Android matrix PASS
9 | Content / AI if applicable | Domain facts, formulas, citations, RAG eval | Critical factual/AI failures = 0
10 | Regression + UAT + final smoke | Freeze critical suite and validate real use | All Release Gates PASS
Interpretation
“MVP RELEASE CANDIDATE” у цьому файлі означає, що всі визначені блокуючі QA-gates пройдені. Це не замінює магазинний review або production monitoring, але дає формальний технічний критерій, що критичні функціональні, data-integrity, security, compatibility та recovery перевірки виконані.

## Analysis Catalog
Каталог видів аналізу для доведення застосунку до MVP
Code | Platform | Вид аналізу | Мета | Що перевіряємо | Коли запускати | Інструменти / підхід | Автоматизація | Ключові метрики | Артефакт на виході | MVP критичність
A01 | Cross-platform | Static code analysis | Знайти дефекти без запуску | Синтаксис, lint, dead code, null/undefined, async errors, type issues, небезпечні патерни | На кожен PR / build | ESLint, TypeScript checks, Semgrep, IDE inspections | Automated | 0 critical lint; 0 blocker findings | Static Analysis Report | High
A02 | Cross-platform | Architecture audit | Перевірити, чи MVP можна підтримувати й розширювати | Шари UI/service/storage/API, state, routing, error handling, конфігурація, модульність | Перед стабілізацією MVP | Code review + dependency map | Manual | Критичні циклічні залежності=0 | Architecture Review | High
A03 | Cross-platform | Dependency / supply-chain audit | Прибрати відомі вразливості та ризикові пакети | CVE, застарілі пакети, abandoned dependencies, ліцензії | Щотижня + перед release | npm audit, OSV, dependency review | Automated | Critical/High exploitable=0 | Dependency Risk Report | High
A04 | Cross-platform | Build configuration audit | Виключити debug/secret/config помилки у release | Dev/prod env, debug flags, source maps, endpoints, feature flags | Кожен release candidate | Build diff + config checklist | Semi-automated | 0 debug-only configs in prod | Build Config Report | High
A05 | Cross-platform | Unit testing | Перевірити окрему бізнес-логіку | Calculators, parsers, validators, transforms, state reducers | На кожну зміну логіки | Jest/Vitest/JUnit equivalents | Automated | 100% critical functions covered | Unit Test Report | High
A06 | Cross-platform | Integration testing | Перевірити взаємодію модулів | UI↔service, parser↔storage, API↔cache, export↔data | На кожен major build | Integration test harness | Automated | Critical integrations pass=100% | Integration Report | High
A07 | Cross-platform | Functional / capability audit | Довести, що кожна функція реально працює end-to-end | Create/read/update/delete, import/export, search, settings, sync | Перед MVP + після великих змін | Manual checklist + automation | Semi-automated | Core capabilities pass=100% | Capability Matrix | Critical
A08 | Cross-platform | End-to-End testing | Перевірити повні сценарії користувача | Install/login/create/import/analyze/save/export/reopen | Кожен release candidate | Playwright/Cypress/Appium/manual | Semi-automated | Critical E2E pass=100% | E2E Report | Critical
A09 | Cross-platform | Negative testing | Перевірити поведінку на неправильних даних | Порожні поля, invalid files, duplicate clicks, timeouts, malformed responses | Перед MVP | Fuzzed/manual scenarios | Semi-automated | 0 crashes; deterministic errors | Negative Test Report | High
A10 | Cross-platform | Boundary / edge-case testing | Знайти дефекти на межах допустимих значень | 0/1/max, very long text, unicode, extremes, date/time edges | Перед MVP | Boundary matrix | Semi-automated | All documented boundaries handled | Boundary Report | High
A11 | Cross-platform | Data integrity audit | Не допустити втрати/дублювання/пошкодження даних | CRUD consistency, referential integrity, export matches source, retries | Кожен RC | Checksums, DB queries, fixture comparison | Semi-automated | Data loss/duplication=0 | Data Integrity Report | Critical
A12 | Cross-platform | Schema / migration testing | Гарантувати безпечне оновлення версій | Old schema→new schema, rollback/forward migration, defaults | Коли змінюється storage/schema | Migration fixtures | Automated | 100% supported migrations pass | Migration Report | Critical
A13 | Cross-platform | Offline-first testing | Перевірити роботу без мережі та відновлення після reconnect | Launch offline, CRUD offline, queue/sync, conflict handling | Кожен RC | Airplane/offline simulation | Semi-automated | Core offline actions pass=100% | Offline Report | Critical
A14 | Cross-platform | Network resilience testing | Перевірити нестабільний інтернет | Latency, packet loss, 429/500, DNS/TLS errors, reconnect | Кожен RC | Network throttling/proxy | Semi-automated | No crash/data loss; clear retry | Network Report | High
A15 | Cross-platform | Crash / recovery testing | Перевірити відновлення після kill/crash | Kill during save/import/export/sync; reopen; state recovery | Кожен RC | Forced process kill + logs | Manual | No corrupted state; recovery path works | Recovery Report | Critical
A16 | Cross-platform | Regression testing | Не допустити повторного ламання виправлених функцій | Critical bug suite + previous feature tests | На кожен build | Automated regression suite | Automated | Critical regression pass=100% | Regression Report | Critical
A17 | Cross-platform | UI visual audit | Знайти візуальні дефекти | Spacing, clipping, overlaps, loaders, empty/error states | Кожен RC | Screenshot review / visual diff | Semi-automated | 0 blocker visual defects | UI Audit | Medium
A18 | Cross-platform | UX / usability audit | Перевірити зрозумілість сценаріїв | Navigation, feedback, discoverability, click count, undo/confirm | Перед UAT | Task-based usability test | Manual | Critical task completion≥90% | UX Findings | High
A19 | Cross-platform | Accessibility audit | Забезпечити базову доступність | Contrast, labels, focus, screen reader, scalable text, touch targets | Перед MVP | Axe/Lighthouse/manual | Semi-automated | No critical accessibility blockers | Accessibility Report | Medium
A20 | Cross-platform | Localization audit | Перевірити всі мови й формати | Missing strings, truncation, pluralization, dates, decimals, units | Кожен RC | Pseudo-localization + manual | Semi-automated | Untranslated critical strings=0 | Localization Report | High
A21 | Cross-platform | Domain/content audit | Перевірити правильність предметної інформації | Rules, formulas, units, warnings, citations, terminology | Перед MVP + при content updates | SME review + test cases | Manual | Critical factual errors=0 | Content Accuracy Report | Critical
A22 | Cross-platform | SAST security audit | Знайти небезпечний код | Injection sinks, unsafe storage, secrets, crypto misuse, insecure APIs | Кожен RC | Semgrep/CodeQL/linters | Automated | Critical/High confirmed=0 | SAST Report | Critical
A23 | Cross-platform | Dynamic security testing | Перевірити runtime attack surface | XSS, injection, auth bypass, API manipulation, malicious input | Перед MVP | OWASP ZAP/Burp/manual | Semi-automated | Critical/High exploitable=0 | DAST Report | Critical
A24 | Cross-platform | Secrets audit | Переконатися, що ключі не потрапили в client/repo/logs | API keys, tokens, service creds, debug dumps | На кожен release | Gitleaks/secret scan | Automated | Exposed production secrets=0 | Secrets Report | Critical
A25 | Cross-platform | Privacy audit | Перевірити мінімізацію та захист даних | PII, telemetry, logs, analytics, retention, consent | Перед launch | Data-flow mapping | Manual | Undocumented sensitive flows=0 | Privacy Review | Critical
A26 | Cross-platform | Authentication / authorization testing | Перевірити доступ і сесії | Login/logout, expired token, role access, direct object access | Кожен RC якщо є auth | API/UI tests | Semi-automated | Unauthorized access=0 | Auth Report | Critical
A27 | Cross-platform | API contract testing | Стабілізувати інтеграції | Schemas, status codes, pagination, idempotency, versioning | На кожен backend/API change | OpenAPI tests, contract fixtures | Automated | Critical contract failures=0 | API Contract Report | High
A28 | Cross-platform | File handling security / robustness | Безпечно обробляти імпорт/експорт | Corrupt/huge files, path traversal, MIME mismatch, unicode names | Перед MVP | Fixture corpus + fuzzing | Semi-automated | No crash/path escape/data loss | File Handling Report | Critical
A29 | Cross-platform | Performance analysis | Перевірити швидкість ключових дій | Startup, list load, parse, search, export, API response | Кожен RC | Profiler + timers | Semi-automated | Meets defined budgets | Performance Report | High
A30 | Cross-platform | Memory leak analysis | Не допустити накопичення RAM | Repeated navigation, import cycles, listeners, caches | Кожен RC | Heap snapshots/profiler | Semi-automated | No unbounded growth | Memory Report | High
A31 | Cross-platform | CPU / rendering analysis | Знайти зайве навантаження | Idle CPU, animations, parsing, rendering spikes | Кожен RC | Profiler/DevTools | Manual | Idle near-zero; no sustained spikes | CPU/GPU Report | Medium
A32 | Cross-platform | Stress / load testing | Знайти межу деградації | Large datasets, files, records, concurrent operations | Перед MVP | Synthetic loads | Semi-automated | Graceful degradation; no corruption | Stress Report | High
A33 | Cross-platform | Observability / logging audit | Забезпечити діагностику без витоку даних | Error logs, correlation IDs, crash traces, log levels, PII masking | Перед MVP | Log review + forced failures | Manual | Actionable logs; sensitive data=0 | Observability Report | High
A34 | PC/Web | Browser compatibility | Перевірити desktop/web runtime | Chrome, Edge, Firefox; supported versions | Кожен RC | Browser matrix | Semi-automated | Critical flows pass on supported browsers | Browser Compatibility Report | High
A35 | PC/Web | Resolution / DPI / scaling audit | Перевірити різні екрани Windows | 1366×768→4K, 100–200% scaling, zoom | Кожен RC | Windows display matrix | Manual | No clipped critical controls | Display Compatibility Report | High
A36 | PC/Web | Keyboard / mouse usability | Перевірити desktop interactions | Tab focus, Enter/Escape, shortcuts, mouse wheel | Кожен RC | Manual / accessibility tools | Manual | All core flows usable | Input UX Report | Medium
A37 | PC/Web | Filesystem/path compatibility | Перевірити реальні Windows paths | Spaces, Cyrillic/Unicode, long paths, read-only dirs | Перед MVP | Fixture paths/files | Semi-automated | No path/encoding failures | Filesystem Report | High
A38 | PC/Web | Windows security environment | Перевірити роботу з Defender/firewall/UAC | Standard user, UAC, blocked network, controlled folders | Перед MVP | Windows VM / policy scenarios | Manual | Graceful handling; no admin dependency unless required | Windows Env Report | High
A39 | PC/Web | Multi-monitor / window-state testing | Перевірити desktop layout | Two monitors, different DPI, resize, maximize/restore | Перед MVP | Manual matrix | Manual | No lost/off-screen dialogs | Windowing Report | Medium
A40 | Android | Android lifecycle testing | Не втрачати стан при lifecycle events | Background/foreground, rotate, lock/unlock, process kill | Кожен RC | ADB + manual/Appium | Semi-automated | No crash/data loss; valid restoration | Lifecycle Report | Critical
A41 | Android | Permission-state testing | Коректно обробляти дозволи | Allow, deny, deny permanently, revoke later, one-time | Кожен RC | ADB/settings/manual | Semi-automated | No crash; actionable UX | Permissions Report | Critical
A42 | Android | Device/OS compatibility | Перевірити заявлену матрицю пристроїв | Small/large phones, OEM skins, min→target Android | Кожен RC | Emulators + physical devices | Semi-automated | Core flows pass on support matrix | Compatibility Matrix | Critical
A43 | Android | WebView/Capacitor compatibility | Перевірити hybrid runtime | WebView updates, plugins, navigation, file APIs, bridges | Кожен RC | Android System WebView matrix | Manual | No bridge/plugin regressions | WebView Report | Critical
A44 | Android | Insets / navigation / rotation | Не ховати UI системними панелями | Gesture nav, 3-button nav, cutout, keyboard, portrait/landscape | Кожен RC | Emulator/device visual matrix | Manual | Critical controls always reachable | Layout Insets Report | High
A45 | Android | Battery / background analysis | Контролювати battery drain | Background tasks, GPS/Bluetooth/network, wakelocks, idle | Перед MVP | Battery Historian / profiler | Manual | No abnormal idle drain | Battery Report | High
A46 | Android | Doze / app standby testing | Перевірити фон і відкладені задачі | Doze, standby, battery saver, delayed jobs, reconnect | Перед MVP | ADB doze commands | Manual | No data loss; expected deferred behavior | Doze Report | High
A47 | Android | Low-memory / process-death testing | Перевірити відновлення після OS kill | Don't keep activities, low RAM, restore navigation/form state | Кожен RC | Developer options + ADB | Manual | No corrupted state | Low-memory Report | Critical
A48 | Android | APK/AAB install/upgrade testing | Гарантувати коректну доставку build | Fresh install, upgrade, reinstall, clear cache/data | Кожен RC | ADB/Play internal test | Semi-automated | Install/upgrade critical paths pass=100% | Install/Upgrade Report | Critical
A49 | Android | Signing / release audit | Перевірити release identity | applicationId, versionCode, signing key, debug flag, minify rules | Кожен release | Gradle/apksigner/bundletool | Semi-automated | Release signed; debug artifacts absent | Signing Report | Critical
A50 | Android | Mobile network transition testing | Перевірити Wi-Fi↔cellular↔offline | Network change during upload/sync/AI request | Кожен RC | Network toggles/proxy | Manual | No stuck state or duplicate action | Mobile Network Report | High
A51 | Android | Notification/deep-link testing | Перевірити зовнішні входи в app | Cold/warm deep link, notification tap, invalid target | Якщо feature існує | ADB/intent tests | Semi-automated | Correct route; safe fallback | Deep-link Report | Medium
A52 | AI/RAG | RAG retrieval evaluation | Перевірити, чи дістається правильне джерело | Known-answer queries, multi-source, no-answer cases | Перед MVP якщо є AI/RAG | Golden dataset + recall metrics | Automated | Critical source recall meets target | RAG Retrieval Report | Critical
A53 | AI/RAG | Citation / groundedness audit | Перевірити, що відповідь підтверджена джерелом | Claim↔citation mapping, stale/irrelevant citation, source conflict | Перед MVP | Golden Q/A + reviewer | Semi-automated | Unsupported critical claims=0 | Groundedness Report | Critical
A54 | AI/RAG | Prompt injection / hostile document test | Не дозволити контенту керувати агентом | Malicious instructions in files/web/RAG chunks | Перед MVP | Injection test corpus | Semi-automated | No unauthorized instruction following | AI Security Report | Critical
A55 | AI/RAG | Hallucination / abstention testing | Перевірити чесну поведінку при відсутності даних | Unknown questions, conflicting sources, ambiguous telemetry | Перед MVP | Adversarial QA set | Semi-automated | Critical hallucinations=0 | Hallucination Report | Critical
A56 | Release | User Acceptance Testing (UAT) | Перевірити продукт на реальних користувачах | Top tasks without guidance, error recovery, satisfaction/blockers | Фінальний етап | 3–10 representative users | Manual | No P0/P1 UAT blockers | UAT Report | Critical
A57 | Release | Release Readiness Audit | Прийняти формальне рішення про RC | Open defects, gate metrics, artifacts, signing, backups, rollback | Перед публікацією | Release checklist + dashboard | Manual | All blocking gates PASS | Release Readiness Report | Critical

## MVP Test Matrix
MVP Test Matrix — конкретні перевірки PC/Web, Android і Cross-platform
Test ID | Platform | Stage | Analysis Type | Subcategory | Що перевірити | Детальний сценарій / кроки | Очікуваний результат / PASS criterion | Інструменти | Automation | Priority | Failure Severity | MVP Gate | Status | Owner | Evidence / Link | Defect ID | Retest | Notes | Frequency
T001 | Cross-platform | 1-Code | Static code analysis | Lint | Critical lint/type errors | Запустити lint/type-check на clean checkout | 0 errors; warnings reviewed | ESLint/TS compiler | Automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every build
T002 | Cross-platform | 1-Code | Secrets audit | Repository | Secrets in repository/history | Scan source + config + recent history for API keys/tokens | No production secrets exposed | Gitleaks/secret scanner | Automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T003 | Cross-platform | 1-Code | Dependency audit | CVE | Known vulnerable dependencies | Run dependency vulnerability scan and triage reachable issues | 0 confirmed Critical/High exploitable issues | npm audit/OSV | Automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T004 | Cross-platform | 1-Code | Architecture audit | Boundaries | UI/business/storage separation | Trace 3 core flows; confirm no uncontrolled direct storage/API calls from UI | Dependencies follow documented architecture | Code review | Manual | P1 | High | NO | NOT STARTED |  |  |  | NOT TESTED |  | Every major release
T005 | Cross-platform | 2-Build | Build config audit | Prod config | Production endpoints and flags | Build release; inspect environment, logs, dev menus, debug flags | Only production-safe config active | Build inspection | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T006 | Cross-platform | 2-Build | Build reproducibility | Clean build | Build from clean checkout | Clear caches/deps as documented; build release artifact | Build succeeds without undeclared local state | CI/local clean build | Automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T007 | Cross-platform | 3-Core | Functional audit | Create | Create primary record/entity | Create valid record using all required fields; save; reopen | Record persists exactly once with correct values | Manual/E2E | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T008 | Cross-platform | 3-Core | Functional audit | Read | Open list/detail of saved record | Restart app; navigate to record; compare values | All persisted fields correct | Manual/E2E | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T009 | Cross-platform | 3-Core | Functional audit | Edit | Edit primary record | Change multiple fields; save; restart | Only intended fields changed; persisted | Manual/E2E | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T010 | Cross-platform | 3-Core | Functional audit | Delete | Delete primary record | Delete; confirm; restart; search for record | Record absent; dependent data handled safely | Manual/E2E | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T011 | Cross-platform | 3-Core | Data integrity | Duplicate action | Double-click/tap Save rapidly | Trigger same action repeatedly | No duplicate record/request | Manual/automation | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T012 | Cross-platform | 3-Core | Negative testing | Required fields | Submit empty/invalid required inputs | Try empty, whitespace-only, invalid formats | Inline error; no invalid data stored | Manual/E2E | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T013 | Cross-platform | 3-Core | Boundary testing | Long text | Very long valid/invalid strings | Paste long text, emoji, UA/EN, symbols into text fields | No crash/layout break; constraints explicit | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Every major release
T014 | Cross-platform | 3-Core | Boundary testing | Numeric limits | 0, negative, max, decimal, huge values | Test documented limits for all critical numeric fields | Validation matches domain rules | Parametrized tests | Automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T015 | Cross-platform | 3-Core | Localization | UA/EN | Language switch and persistence | Switch language mid-flow; restart app | No mixed critical UI; selection persists | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T016 | Cross-platform | 3-Core | Localization | Formats | Date/number/unit formats | Check decimal separators, dates, time zone, units in UI/export | Meaning preserved; no silent value changes | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T017 | Cross-platform | 4-Data | Import testing | Valid file | Import supported file | Import known-good fixture; compare parsed records | Parsed output exactly matches fixture ground truth | Fixture tests | Automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T018 | Cross-platform | 4-Data | Import testing | Corrupt file | Import truncated/corrupt file | Use corrupt/empty/wrong MIME fixtures | Clear error; no partial corruption | Fixture tests | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T019 | Cross-platform | 4-Data | File security | Huge file | Import file near/above supported size | Load large fixture and observe memory/error path | Graceful limit or successful import; no crash | Profiler + fixture | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T020 | Cross-platform | 4-Data | File compatibility | Unicode path/name | Use filenames with spaces, Cyrillic, emoji, long names | Prepare representative files with spaces, Cyrillic, emoji and long names; run import and export for each supported format. | Import/export succeeds or documented validation | Fixture files | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T021 | Cross-platform | 4-Data | Export testing | Content parity | Export PDF/CSV/XLSX/JSON as applicable | Create known fixture; export; compare key values | Export matches source values/units/order | Diff/checksum | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T022 | Cross-platform | 4-Data | Export testing | Repeat export | Export same record repeatedly | Run export 10x; open each artifact | All artifacts valid; no state leak | Manual/automation | Semi-automated | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Every major release
T023 | Cross-platform | 4-Data | Migration testing | Old version data | Install/load previous schema then current build | Upgrade without clearing data | All supported user data survives migration | Migration fixtures | Automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T024 | Cross-platform | 4-Data | Crash recovery | Kill during save | Force process close while saving | Reopen and inspect consistency | No corrupted/half-linked data | Forced kill | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T025 | Cross-platform | 4-Data | Crash recovery | Kill during import | Terminate during long import | Reopen app; inspect temp/partial records | Safe rollback/resume; no corrupt DB | Forced kill | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T026 | Cross-platform | 5-Network | Offline | Cold launch offline | Disable network before launch | Start from a closed app with network disabled; launch and open the core offline screens/data required by the product design. | Core offline UI/data accessible as designed | Network off | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T027 | Cross-platform | 5-Network | Offline | Create/edit offline | Perform critical offline CRUD | Create/edit/save; restart still offline | Changes persist locally | Network off | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T028 | Cross-platform | 5-Network | Reconnect | Sync after offline work | Create offline changes; reconnect | While offline, create/edit representative records; restore network; observe sync, local state and server state. | Single correct sync; no duplicates/data loss | Proxy/logs | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T029 | Cross-platform | 5-Network | Conflict handling | Concurrent/conflicting edits | Create conflicting edits and reconnect | Create conflicting edits to the same record in two states/clients, reconnect, and verify the documented conflict-resolution policy. | Conflict resolved by documented policy | Test harness | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T030 | Cross-platform | 5-Network | HTTP failures | 429/500/timeouts | Inject API 429/500/timeout responses | Mock 429, 500 and timeout responses during core network actions; retry where offered and inspect resulting state. | User sees actionable error/retry; state consistent | Proxy/mock server | Automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T031 | Cross-platform | 5-Network | Malformed API | Invalid response schema | Return missing/wrong fields | Return responses with missing fields, wrong types and malformed payloads during core API flows. | No crash; error logged; safe fallback | Mock server | Automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T032 | Cross-platform | 6-Security | Input security | Injection/XSS-like payloads | Enter script/SQL/meta chars in text inputs/imported content | Submit representative script/SQL/metacharacter payloads through text inputs and imported content; inspect rendering, storage and execution behavior. | Content treated as data; no execution | Security payload corpus | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T033 | Cross-platform | 6-Security | Storage security | Sensitive data at rest | Inspect local DB/storage/logs/cache after normal use | Use the app with representative sensitive values, then inspect local DB/storage/logs/cache for plaintext or unnecessary persistence. | No secrets/plain sensitive data beyond design | Manual inspection | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T034 | Cross-platform | 6-Security | Logging privacy | PII/secrets in logs | Trigger errors and inspect logs | Trigger representative validation, network and runtime errors; inspect all generated logs and diagnostic output. | Tokens/secrets/sensitive payloads absent or redacted | Log review | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T035 | Cross-platform | 6-Security | Authorization | Direct object access | Manipulate ID/route/API request if accounts/roles exist | If IDs/roles exist, alter object IDs/routes/API requests under a user lacking access and attempt direct access. | Unauthorized data inaccessible | API/UI security test | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T036 | Cross-platform | 6-Security | Session handling | Expired/revoked session | Expire token during use | Invalidate or expire the active session during an unsaved/core operation; continue navigation/save attempts and re-authenticate. | Safe re-auth; unsaved data handled predictably | Mock/auth env | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T037 | Cross-platform | 7-Performance | Startup | Cold start budget | Measure 10 cold starts on reference device/PC | From a consistent cold state, perform 10 launches on the reference PC/device; record each startup duration and calculate median/p95. | Median and p95 within chosen budget | Profiler/timer | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T038 | Cross-platform | 7-Performance | Core action latency | Open list/detail/search | Measure representative dataset | Load a representative dataset and measure latency for the defined core actions under the same reference environment. | UI remains responsive; budget met | Profiler | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T039 | Cross-platform | 7-Performance | Large dataset | High record count | Load dataset at expected high-end + 2x | Generate datasets at the expected high-end and 2x size; execute core load/search/edit/export flows while recording responsiveness and failures. | No crash; acceptable degradation | Synthetic dataset | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T040 | Cross-platform | 7-Performance | Memory leak | Navigation loop | Repeat key screen cycle 100x; take heap snapshots | Repeat the defined navigation cycle 100 times, taking baseline/intermediate/final heap snapshots and allowing idle/GC between checkpoints. | No unbounded retained growth | Heap profiler | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T041 | Cross-platform | 7-Performance | Memory leak | Import/export loop | Repeat import/export sequence | Repeat a representative import/export cycle multiple times; capture memory before, during and after idle/GC. | Memory returns near baseline after idle/GC | Profiler | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T042 | Cross-platform | 8-UX | Error UX | Recoverable failure | Force network/file validation error | Force representative network and file-validation failures from core flows; verify the message, recovery action and preserved state. | Message explains problem + next action; no dead end | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T043 | Cross-platform | 8-UX | Empty states | Fresh account/install | Open all data screens with no records | Use a fresh install/account with zero records; open each primary data screen and attempt the intended first action. | Clear CTA and no broken layout | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T044 | Cross-platform | 8-UX | Loading states | Slow operations | Throttle CPU/network; run import/API calls | Throttle CPU/network and run slow import/API operations; attempt repeated taps/clicks while the operation is pending. | Loading visible; duplicate actions prevented | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T045 | Cross-platform | 8-UX | Accessibility | Keyboard/focus/labels | Navigate core screens with keyboard/screen reader where supported | Traverse every core flow using keyboard and, where supported, a screen reader; inspect focus order, labels and activation. | Critical controls named and reachable | Axe/manual | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T046 | Cross-platform | 8-UX | Accessibility | Text scaling | Increase text/system scaling | Increase OS/browser text or display scaling to supported high settings; run the critical flows and inspect clipping/overlap. | Core actions remain visible and usable | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
T047 | Cross-platform | 9-Content | Domain audit | Formula correctness | Compare critical formulas against validated examples | Select representative critical formula cases including boundaries; calculate expected results independently and compare app output within the defined tolerance. | Known inputs produce exact expected outputs | Golden fixtures + reviewer | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T048 | Cross-platform | 9-Content | Domain audit | Warnings/limits | Verify warnings shown at correct point | Trigger each relevant condition | Correct warning and blocking behavior | Manual | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T049 | Cross-platform | 9-Content | Citations/sources | Source integrity | Open source references for critical claims | Open every source used by critical domain claims; compare the claim, source content and cited version/date. | Citation/source matches claim/version | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
T050 | Cross-platform | 10-Regression | Critical regression | Known critical flows | Run frozen critical suite after fixes | Execute the frozen critical regression suite against the candidate build after fixes; record every case and failure. | 100% pass | CI/E2E suite | Automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every build
P001 | PC/Web | 11-PC | Browser compatibility | Chrome | Supported Chrome | Run all critical flows | 100% critical flow pass | Playwright/manual | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P002 | PC/Web | 11-PC | Browser compatibility | Edge | Supported Edge | Run all critical flows | 100% critical flow pass | Playwright/manual | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P003 | PC/Web | 11-PC | Browser compatibility | Firefox | Supported Firefox if in scope | Run all critical flows | 100% critical pass or explicitly unsupported | Playwright/manual | Semi-automated | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P004 | PC/Web | 11-PC | Display compatibility | 1366×768 | Low desktop resolution | Run top 10 screens at 1366×768 | No hidden/overlapping critical controls | Manual/screenshots | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P005 | PC/Web | 11-PC | Display compatibility | 1920×1080 | Reference desktop resolution | Run top 10 screens | Layout stable; no clipping | Manual/screenshots | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P006 | PC/Web | 11-PC | Display compatibility | 4K + scaling | 4K at 150–200% Windows scaling | Run critical screens | No tiny/unreachable/clipped critical UI | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P007 | PC/Web | 11-PC | Window behavior | Resize | Continuous resize | Resize through breakpoints | Layout adapts; no unusable breakpoint | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P008 | PC/Web | 11-PC | Window behavior | Multi-monitor | Move across monitors with different DPI | Open dialogs and move app | Dialogs remain visible and correctly positioned | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P009 | PC/Web | 11-PC | Keyboard usability | Tab order | Complete core flow without mouse | Use Tab/Shift+Tab/Enter | Logical focus and visible focus state | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P010 | PC/Web | 11-PC | Keyboard usability | Enter/Escape | Submit/cancel/modal behavior | Test Enter/Escape in forms/modals | No accidental destructive action | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P011 | PC/Web | 11-PC | Clipboard | Paste large/unicode | Paste multiline/unicode/long values | Use forms and editors | No crash; validation works | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P012 | PC/Web | 11-PC | Filesystem | Spaces in path | Import/export from path with spaces | Use nested folder path | Operation succeeds | Fixture folders | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P013 | PC/Web | 11-PC | Filesystem | Cyrillic/Unicode path | Use Cyrillic/emoji in names | Import/export/read files | Operation succeeds or clear limitation | Fixture folders | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P014 | PC/Web | 11-PC | Filesystem | Read-only destination | Export to non-writable folder | Attempt export | Clear error; no crash/partial file | Windows ACL | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P015 | PC/Web | 11-PC | Windows environment | Standard user | Run without administrator | Install/run normal flows | No elevation dependency unless documented | Windows account | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
P016 | PC/Web | 11-PC | Windows environment | Firewall blocked | Block outbound app traffic | Run online features | Offline/error UX works; no freeze | Windows Firewall | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P017 | PC/Web | 11-PC | Windows environment | Defender | Default Windows Defender | Install/run/scan artifact | No unexplained block; false positives investigated | Windows Defender | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P018 | PC/Web | 11-PC | Power/session | Sleep/wake | Sleep during idle and active screen | Resume after sleep | State/session consistent | Manual | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P019 | PC/Web | 11-PC | Power/session | Adapter reset | Disable/enable network adapter mid-request | Retry/reopen | Request fails/retries safely | Manual | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
P020 | PC/Web | 11-PC | Browser storage | Cache/storage reset | Clear cache or site data per scenario | Relaunch | Behavior matches persistence design | DevTools | Manual | P2 | Medium | NO | NOT STARTED |  |  |  | NOT TESTED |  | Before MVP
A001 | Android | 12-Android | Install/upgrade | Fresh install | Install release APK/AAB | Install on clean device; first launch | Install/launch succeeds; default state valid | ADB/internal testing | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A002 | Android | 12-Android | Install/upgrade | Upgrade | Upgrade from previous build | Create data on old build; install new build | App launches; user data/settings preserved | ADB/internal testing | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A003 | Android | 12-Android | Install/upgrade | Clear cache | Clear cache only | Relaunch | Persistent data remains as designed | Settings/ADB | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A004 | Android | 12-Android | Install/upgrade | Clear app data | Clear all app data | Launch clean | Valid onboarding/defaults; no broken remote state | Settings/ADB | Manual | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A005 | Android | 12-Android | Lifecycle | Background/foreground | Home and return | Start core task; Home; return | State restored; no duplicate action/crash | ADB/manual | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A006 | Android | 12-Android | Lifecycle | Lock/unlock | Lock on form/result | Unlock | State valid; privacy behavior appropriate | Manual | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A007 | Android | 12-Android | Lifecycle | Rotation | Rotate critical screens | Portrait↔landscape | No crash/data loss/layout overlap | Emulator/device | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A008 | Android | 12-Android | Lifecycle | Process death | OS/process kills activity | Use Don't keep activities or kill background process | App restores or safely returns to consistent state | Developer options/ADB | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A009 | Android | 12-Android | Lifecycle | Kill during save | Force-stop at save boundary | Reopen | No corrupted storage; deterministic state | ADB | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A010 | Android | 12-Android | Permissions | Allow | Grant each runtime permission | Use dependent feature | Feature works; no bad prompt loop | Device/settings | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A011 | Android | 12-Android | Permissions | Deny | Deny each runtime permission | Try dependent feature | No crash; clear limited-function UX | Device/settings | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A012 | Android | 12-Android | Permissions | Deny permanently | Permanent denial | Retry feature | App offers Settings path; no infinite prompt | Device/settings | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A013 | Android | 12-Android | Permissions | Revoke later | Grant then revoke | Return to feature | Revocation detected safely | Device/settings | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A014 | Android | 12-Android | Layout | Gesture navigation | Use gesture nav | Run all critical screens | Bottom controls not covered; back gesture sensible | Physical/emulator | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A015 | Android | 12-Android | Layout | 3-button navigation | Use 3-button nav | Run critical screens | Bottom controls visible | Physical/emulator | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A016 | Android | 12-Android | Layout | Keyboard open | Focus bottom field | Open keyboard and submit | Field/action scrolls above keyboard | Physical/emulator | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A017 | Android | 12-Android | Layout | Cutout/insets | Notch/cutout device | Open header/modal/fullscreen screens | UI respects safe areas | Emulator | Manual | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A018 | Android | 12-Android | Layout | Small phone | Smallest supported viewport | Run critical flows | All core controls usable | Emulator/device | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A019 | Android | 12-Android | Layout | Large font | Increase font/display size | Run forms/navigation | Critical text/buttons usable | Android settings | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A020 | Android | 12-Android | Compatibility | Minimum supported Android | Min OS | Run critical suite | 100% critical suite pass | Emulator/device | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A021 | Android | 12-Android | Compatibility | Target/current supported Android | Target OS | Run critical suite | 100% critical suite pass | Emulator/device | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A022 | Android | 12-Android | Compatibility | OEM variation | Non-stock OEM | Run smoke + critical flows | No OEM-specific blocker | Physical device | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A023 | Android | 12-Android | WebView/Capacitor | Bridge actions | Native bridge/plugin calls | Test file/share/permission/native calls | All resolve correctly | Logcat/manual | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A024 | Android | 12-Android | WebView/Capacitor | WebView update | System WebView update | Update/restart and run critical flows | No blank screen/plugin regression | Physical/emulator | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A025 | Android | 12-Android | Network | Wi-Fi→cellular | Switch during active request | Observe request/state | No duplicate/stuck operation | Device/manual | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A026 | Android | 12-Android | Network | Online→offline | Disable network during sync/request | Continue app use | Clear failure state; safe local data | Device/manual | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A027 | Android | 12-Android | Network | Offline→online | Reconnect after offline edits | Observe sync | Sync once; no duplication | Device/manual | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A028 | Android | 12-Android | Battery | Idle drain | Foreground/background idle | Measure controlled period | No abnormal sustained CPU/network/wakelock | Profiler/Battery Historian | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A029 | Android | 12-Android | Background | Doze mode | Force Doze | Queue background work then Doze | Deferred/resumed as designed; no data loss | ADB doze | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A030 | Android | 12-Android | Background | Battery saver | Enable saver | Use app normally | Foreground stable; background behavior documented | Device/ADB | Manual | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A031 | Android | 12-Android | Low memory | Don't keep activities | Destroy activities repeatedly | Navigate/forms | No state corruption/crash | Developer options | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A032 | Android | 12-Android | Storage | Low free space | Reduce available storage | Import/export/save | Graceful error before corruption | Emulator/ADB | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A033 | Android | 12-Android | Sharing | Share/export target | Share generated artifact | Use share sheet then cancel/select app | Correct MIME/name/content; cancel safe | Android share sheet | Manual | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
A034 | Android | 12-Android | Back navigation | System back | Back from every critical screen/modal | Use gesture/button back | No accidental exit/data loss | Manual | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A035 | Android | 12-Android | Cold start | After force-stop | Force-stop then launch 10x | Repeat | No intermittent blank screen/crash | ADB/manual | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A036 | Android | 12-Android | Logging | Logcat | Trigger major failures | Inspect logcat | Actionable logs without secrets/PII | Logcat | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A037 | Android | 12-Android | Release signing | Identity/signature | Verify package ID/version/signature/debug flag | Inspect release artifact | Correct production identity; debug=false | apksigner/bundletool | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
A038 | Android | 12-Android | Deep links | Cold/warm start | Open valid/invalid app links if used | Test cold/warm states | Correct route or safe fallback | ADB intents | Semi-automated | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | If feature changes
A039 | Android | 12-Android | Notifications | Permission/tap | Allow/deny and tap notification if used | Test cold/warm states | No crash; correct destination | Device/ADB | Manual | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | If feature changes
A040 | Android | 12-Android | Touch | Rapid taps | Rapid CTA/navigation taps | Tap repeatedly | No duplicate request/navigation corruption | Manual | Manual | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Every release
AI001 | AI/RAG | 13-AI | Retrieval | Known-answer | Golden questions | Run queries with known source chunks | Correct source retrieved for critical queries | Eval harness | Automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | After model/index change
AI002 | AI/RAG | 13-AI | Retrieval | Multi-source | Question requiring 2–3 sources | Run multi-source query | Relevant sources combined; conflicts surfaced | Eval harness | Semi-automated | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | After model/index change
AI003 | AI/RAG | 13-AI | Groundedness | Citation mapping | Claims vs citations | Verify each critical claim against cited text | All critical claims supported | Reviewer/eval | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | After model/index change
AI004 | AI/RAG | 13-AI | Hallucination | No-answer | Missing knowledge | Ask outside KB | Model abstains/labels uncertainty; no fake citation | Eval harness | Automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | After model/index change
AI005 | AI/RAG | 13-AI | Security | Prompt injection | Hostile retrieved document | Insert malicious instructions in source chunk | Model ignores document-level control instructions | Injection corpus | Semi-automated | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
AI006 | AI/RAG | 13-AI | Safety | Conflicting sources | Source conflict | Provide two conflicting sources | Response identifies conflict and limitations | Eval harness | Semi-automated | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
AI007 | AI/RAG | 13-AI | Latency | Response time | p50/p95 AI latency | Run representative requests | Within UX budget; timeout path works | Telemetry | Automated | P2 | Medium | NO | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Periodic
AI008 | AI/RAG | 13-AI | Privacy | Prompt payload | Outbound AI data | Inspect request/logs | Only required data sent; secrets/PII handled | Proxy/log review | Manual | P0 | Critical | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
AI009 | AI/RAG | 13-AI | Rate limits | 429 | Force rate-limit | Observe fallback/retry | Controlled UX; no duplicate billing action | Mock/API | Semi-automated | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | Before MVP
AI010 | AI/RAG | 13-AI | Regression | Golden eval | Frozen eval suite | Run after prompt/model/index change | No critical regression beyond threshold | Eval harness | Automated | P1 | High | YES | N/A |  | Out of MVP scope per user decision 2026-09-24: MVP is Windows desktop offline app only (no Android/AI). See work/AUDIT_STATE.json scope_decision. |  | N/A |  | After model/index change
R001 | Release | 14-UAT | UAT | First-use | New user primary task | Observe 3–10 users without coaching | ≥90% complete critical task; no P0/P1 blocker | Moderated UAT | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | One-time before launch
R002 | Release | 14-UAT | UAT | Error recovery | Seeded recoverable error | Observe user response | User understands and recovers without external help | Moderated UAT | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | One-time before launch
R003 | Release | 15-Release | Release readiness | P0 defects | Open P0 review | Review defect register | 0 open P0 defects | Defect tracker | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
R004 | Release | 15-Release | Release readiness | P1 defects | Open P1 review | Review defect register | 0 open P1 in MVP-critical scope | Defect tracker | Manual | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
R005 | Release | 15-Release | Release readiness | Evidence | Blocking gate evidence | Verify reports/evidence | Every blocking gate has evidence/owner | Checklist | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
R006 | Release | 15-Release | Release readiness | Rollback/recovery | Bad release plan | Document and simulate rollback/recovery | Plan actionable and tested/simulated | Release runbook | Manual | P1 | High | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release
R007 | Release | 15-Release | Release readiness | Final smoke | Release candidate smoke | Install RC and run 10-minute smoke | All smoke tests pass on target platforms | Smoke suite | Semi-automated | P0 | Critical | YES | NOT STARTED |  |  |  | NOT TESTED |  | Every release

## Defects
Defect Register — баги, блокери та ретест
Defect ID | Test ID | Platform | Title | Steps to reproduce | Expected | Actual | Severity | Priority | Reproducibility | Status | Owner | Found Build | Fixed Build | Retest | Evidence | Notes | Release Blocker
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO
[10 empty] | OPEN |  |  |  | NOT TESTED |  |  | NO

## Test Runs
Test Run Log — історія перевірок build-ів
Run ID | Date | Build / Commit | Platform / Device | OS / Browser / WebView | Environment | Tester | Scope | Total | Pass | Fail | Blocked | Duration | Notes
RUN-20260924-GUARDS | 2026-09-24 | main 793dc08 | Windows x64 / seed DB + fixture DB | Windows 11 / Python 3.13 | local | manager | calculator guards + persistence (fixture DB); production-DB tests blocked on seed DB | 17 | 11 | 0 | 6 | ~5s | 6 blocked: seed DB has 0 models, production DB only in private release v3.3.0

## Release Gate
Release Gate — мінімальні умови для MVP Release Candidate
Gate ID | Blocking Gate | Required threshold | Current value | Result | Why it matters | Action if FAIL
G01 | Open P0 defects | 0 |  |  | P0 = crash/data loss/security/release blocker | Do not release; fix or remove affected scope
G02 | Open P1 defects | 0 |  |  | P1 breaks major user flow or reliability | Fix before MVP unless scope removed
G03 | Failed MVP-gate tests | 0 |  |  | Blocking tests must not fail | Fix defect and retest
G04 | Blocked MVP-gate tests | 0 |  |  | Unknown critical state is not release-ready | Unblock environment/dependency and execute
G05 | Untested MVP-gate tests | 0 |  |  | Critical coverage must be complete | Finish all blocking tests
G06 | P0 test failures | 0 |  |  | P0 failures represent unacceptable MVP risk | Fix and rerun regression
G07 | Android gate failures | 0 |  |  | Android release must pass lifecycle/install/data critical paths | Fix and retest on device matrix
G08 | PC/Web gate failures | 0 |  |  | PC/Web target must pass supported environment | Fix compatibility or remove unsupported target
G09 | Cross-platform gate failures | 0 |  |  | Core product logic/data/security applies everywhere | Fix before RC
G10 | Final smoke test | PASS |  |  | Final artifact must install and complete smoke flow | Rebuild/retest RC
G11 | Workbook structural integrity errors | 0 |  |  | Malformed enums, missing gate fields, duplicate/orphan rows or shifted columns can invalidate release counts | Repair workbook structure and recompute all gate inputs from raw rows
G12 | Open Critical defects | 0 |  |  | A Critical defect in required MVP scope is release-blocking regardless of priority label | Resolve, verify and close the Critical defect
G13 | Open ReleaseBlocker defects | 0 |  |  | ReleaseBlocker=YES independently blocks the release decision | Resolve and verify every open release blocker
G14 | MVP-gate N/A without evidence | 0 |  |  | N/A cannot remove a required gate without objective documented evidence | Add objective applicability evidence or execute/fix the test
MVP Gate Summary
Blocking gates passed
Blocking gates total
Gate pass ratio
Release decision

## Lists
Status | Priority | Severity | Automation | MVP Gate | Retest | Platform | Frequency | Release Blocker
NOT STARTED | P0 | Critical | Manual | YES | NOT TESTED | Cross-platform | Every release | YES
IN PROGRESS | P1 | High | Semi-automated | NO | PASS | PC/Web | Every major release | NO
PASS | P2 | Medium | Automated |  | FAIL | Android | After related change
FAIL | P3 | Low |  |  | N/A | Backend/API | Before MVP
BLOCKED | [5 empty] | AI/RAG | Periodic
N/A | [5 empty] | Release | One-time before launch
Every build
If feature changes
After model/index change